## Project Backlog
UPDATED BACKLOG
1 | Microcontrollers | 5
2 | Swtiches & Buttons | 1
3 | LCD Display | 2
4 | LED Indicators | 1
5 | Vibration Indicator | 1
6 | RSSI Indication | 5
7 | Antenna Array | 5
8 | Power Module | 3
9 | Battery | 2
10 | LoRa Research | 3
11 | Define Power Constraints | 2
12 | Select IDE to use | 3
13 | Design a wiring schematic | 2
14 | Map out Connections | 2
15 | Design Power Module and Implement on a Breadboard | 5
16 | Solder PowerModule and Power Circuits to Breadboard | 3
17 | Test Both Micocontroller Funcionality | 2
18 | Test Microcontroller Communication | 6
19 | Design Interface for LCD | 2
20 | Flowchart/Psuedo code LCD | 2
21 | Write Program for LCD | 2
22 | Test LCD output: Hello World | 2
23 | Design Interface for LEDs | 2
24 | Flowchart/Psuedo code LEDs | 2
25 | Write Program for LEDs | 2
26 | Design Interface for Switches | 2
27 | Flowchart/Psuedo code Switches | 2
28 | Write Program for Switches | 2
29 | Use switches to control LEDs | 2
30 | Interface Wio-WM1110 with uC | 5
31 | Establish mesh network using uC | 15
32 | Test Tx and Rx signal strength on the mesh | 5
34 | Flowchart/Psuedo code Mesh | 2
35 | Design Interface for Virbation Indicator | 1
36 | Flowchart/Psuedo code Virbation Indicator | 1
37 | Write Program for Virbation Indicator | 3
38 | Design Interface for Buttons | 2
39 | Flowchart/Psuedo code Buttons | 2
40 | Write Program for Buttons | 2
41 | Integrate wm-1110 with PI | 8
42 | Integrate rp2040 with PI | 6
43 | Test communication wm 1110 to PI | 2
44 | Test communication rp2040 to PI | 2
45 | Test LCD on Breadboard | 2
46 | Test LEDs on Breadboard | 6
47 | Test Swithces on Breadboard | 2
48 | Test Virbation Indicator on Breadboard | 2
49 | Test Buttons on Breadboard | 2
50 | Solder and test components | 2
51 | Add LCD to Protoboard | 2
52 | Add LEDs to Protoboard | 10
53 | Add Switches to Protoboard | 2
54 | Add Buttons to Protoboard | 2
55 | Add Vibration Indication to Protoboard | 2
56 | Create a second device for the purpose of testing | 2
57 | Flowchart/Psuedo code Rx Signal Strength Indicator on PI | 2
58 | Write Program for Rx Signal Strength Indicator on PI | 2
59 | Test signal strength input as an output to rp 2040 | 5
66 | Output the signal to LCD using a device ID | 5
68 | Program ability to classify IDs based on switch input | 5
69 | Define power constraits and create power rail for all devices (batteries) | 5
73 | Soldering second device | 5
75 | Test automatic communication of Uc's | 3
76 | Test automatic startup of Uc after switched on | 3
78 | Program output for the LCD device to handle RSSI and device IDs | 5
79 | Device power research | 5
80 | Write code to send the hex value through UART to radio board | 5
81 | Write code to Tx hex value and Rx and pass along all Rx values | 2
82 | Write code to compare the set hex value with Rx hex values | 4
83 | Write code to display matches to LCD | 5
84 | Test Uart transmissions | 3
85 | Test RSSI transmissions | 3
86 | Test LCD outputs with real data | 5
87 | Test switch input program | 5
88 | RF interference testing | 2
89 | RF Distance and Coverage testing | 3
90 | Latency Testing | 2
91 | Packet loss and error rate testing | 2
92 | Field Testing | 3
Total hours
256

## Sprint 1 Backlog
Task Number | Hours | Task Description
1 | 5 | Microcontrollers
2 | 1 | Swtiches & Buttons
3 | 2 | LCD Display
4 | 1 | LED Indicators
5 | 1 | Vibration Indicator
6 | 5 | RSSI Indication
7 | 5 | Antenna Array
8 | 3 | Power Module
9 | 2 | Battery
10 | 3 | LoRa Research
11 | 2 | Define Power Constraints
12 | 3 | Select IDE to use
13 | 2 | Design a wiring schematic
14 | 2 | Map out Connections
15 | 5 | Design Power Module and Implement on a Breadboard
16 | 3 | Solder PowerModule and Power Circuits to Breadboard
17 | 2 | Test Both Micocontroller Funcionality
18 | 6 | Test Microcontroller Communication
19 | 2 | Design Interface for LCD
20 | 2 | Flowchart/Psuedo code LCD
21 | 2 | Write Program for LCD
22 | 2 | Test LCD output: Hello World
23 | 2 | Design Interface for LEDs
24 | 2 | Flowchart/Psuedo code LEDs
25 | 2 | Write Program for LEDs
26 | 2 | Design Interface for Switches
27 | 2 | Flowchart/Psuedo code Switches
28 | 2 | Write Program for Switches
29 | 2 | Use switches to control LEDs
30 | 5 | Interface Wio-WM1110 with uC
31 | 5 | Establish mesh network using uC
32 | 5 | Test Tx and Rx signal strength on the mesh
Total Hours =
90

## Sprint 2 Backlog
Task Number | Task Description | Hours
32 | Establish mesh network using uC | 15
33 | Test Tx and Rx signal strength on the mesh | 2
34 | Flowchart/Psuedo code Mesh | 2
35 | Design Interface for Virbation Indicator | 1
36 | Flowchart/Psuedo code Virbation Indicator | 1
37 | Write Program for Virbation Indicator | 3
38 | Design Interface for Buttons | 2
39 | Flowchart/Psuedo code Buttons | 2
40 | Write Program for Buttons | 2
41 | Integrate wm-1110 with PI | 8
42 | Integrate rp2040 with PI | 6
43 | Test communication wm 1110 to PI | 2
44 | Test communication rp2040 to PI | 2
45 | Test LCD on Breadboard | 2
46 | Test LEDs on Breadboard | 6
47 | Test Swithces on Breadboard | 2
48 | Test Virbation Indicator on Breadboard | 2
49 | Test Buttons on Breadboard | 2
50 | Solder and test components | 2
51 | Add LCD to Protoboard | 2
52 | Add LEDs to Protoboard | 10
53 | Add Switches to Protoboard | 2
54 | Add Buttons to Protoboard | 2
55 | Add Vibration Indication to Protoboard | 2
56 | Create a second device for the purpose of testing | 2
57 | Flowchart/Psuedo code Rx Signal Strength Indicator on PI | 2
58 | Write Program for Rx Signal Strength Indicator on PI | 2
59 | Test signal strength input as an output to rp 2040 | 5
Total Hours =
93

## Sprint 3 Backlog
Task Number | Task Description | Hours
33 | Test Tx and Rx signal strength of Uc | 5
34 | Flowchart/Psuedo code Mesh | 5
57 | Write program for Rx and Tx of Uc | 5
58 | Flowchart/Psuedo code Rx Signal Strength Indicator on PI | 1
59 | Write Program for Rx Signal Strength Indicator on PI | 3
60 | Interface with waveshare LCD | 1
61 | Write a useful image output for LCD | 4
62 | Write code for radar display for LCD | 5
62 | Write Uart program for PI | 3
63 | Write Uart program for Wio | 3
64 | Test Uart communication | 5
65 | Rx and send a Uart signal to the PI | 5
66 | Output the signal to LCD using a device ID | 5
67 | Design Program flow to handle IDs | 5
68 | Program ability to classify IDs based on switch input | 10
69 | Define power constraits and create power rail for all devices (batteries) | 5
70 | Protoboard a second device | 10
71 | Second Protoboard design | 10
72 | Test programs on Wio Uc | 10
73 | Solder a second device | 10
74 | Test automatic communication of Uc's | 3
76 | Test automatic startup of Uc after switched on | 3
77 | Design PCB | 10
|  | Total Hours = | 126

## Sprint 4 Backlog
Task Number | Task Description | Hours
66 | Output the signal to LCD using a device ID | 5
68 | Program ability to classify IDs based on switch input | 5
69 | Define power constraits and create power rail for all devices (batteries) | 5
73 | Soldering second device | 5
75 | Test automatic communication of Uc's | 3
76 | Test automatic startup of Uc after switched on | 3
78 | Program output for the LCD device to handle RSSI and device IDs | 5
79 | Device power research | 5
80 | Write code to send the hex value through UART to radio board | 5
81 | Write code to Tx hex value and Rx and pass along all Rx values | 2
82 | Write code to compare the set hex value with Rx hex values | 4
83 | Write code to display matches to LCD | 5
84 | Test Uart transmissions | 3
85 | Test RSSI transmissions | 3
86 | Test LCD outputs with real data | 5
87 | Test switch input program | 5
88 | RF interference testing | 2
89 | RF Distance and Coverage testing | 3
90 | Latency Testing | 2
91 | Packet loss and error rate testing | 2
92 | Field Testing | 3
Total hours
80

## Sprint 4.5 Backlog
Task Number | Task Description | Hours
93 | Design Power Rail | 4
94 | Test Power Rail | 4
95 | Add directionality to display | 4
96 | Test Directionality | 4
97 | Test stability and remove old IDs | 4
Total Hours =
20